## 1st pres gantt chart
Task Name | Start | Finish | Duration | Assigned To
Capstone Announcement | 2021-06-15 | 2021-06-15 | 1
Problem Definition | 2021-06-15 | 2021-06-28 | 14
Literature Review on previous works | 2021-06-28 | 2021-07-13 | 16
Background Research on Tracking Technologies | 2021-06-28 | 2021-07-13 | 16 |  | 44362 | 44551
iBeacons and Eddystone | 2021-06-28 | 2021-07-13 | 16 | Smriti
Free Public Wifi | 2021-06-28 | 2021-07-13 | 16 | Letao
Sharing bikes and scooters | 2021-06-28 | 2021-07-13 | 16 | Anbo
Local Tracking technologies in China | 2021-06-28 | 2021-07-13 | 16 | Rachel
Other Technologies | 2021-06-28 | 2021-07-13 | 16 | Claudia
First Report and Presentation | 2021-07-06 | 2021-07-06 | 1
Product Planning | 2021-07-13 | 2021-07-27 | 15
Product Design | 2021-07-27 | 2021-08-10 | 15
Second Report and Presentation | 2021-08-10 | 2021-08-10 | 1
Product Development | 2021-08-11 | 2021-10-12 | 63
Product Testing | 2021-10-12 | 2021-11-02 | 22
Product Go Live & Data Collection | 2021-11-02 | 2021-11-30 | 29
Data Analysis | 2021-11-30 | 2021-12-21 | 22
Product Development | 2021-07-13 | 2021-12-21 | 162

## 2nd pres gantt chart
Task Name | Start | Finish | Duration | Assigned To
Capstone Announcement | 2021-06-15 | 2021-06-15 | 1
Problem Definition | 2021-06-15 | 2021-06-28 | 14
Literature Review on previous works | 2021-06-28 | 2021-08-10 | 44
Background Research on Beacon Technology | 2021-06-28 | 2021-08-31 | 65
First Report and Presentation | 2021-07-06 | 2021-07-06 | 1
Research on Provider Companies and Beacon Unique ID | 2021-06-28 | 2021-08-31 | 65
Research on Information Flow Ecosystem | 2021-07-26 | 2021-08-31 | 37
Product Demos | 2021-07-15 | 2021-08-31 | 48
Database Collection Server Development* | 2021-08-01 | 2021-08-05 | 5
Data Collection | 2021-08-04 | 2021-11-30 | 119
Second Report and Presentation | 2021-08-10 | 2021-08-10 | 1
App Modification | 2021-08-11 | 2021-09-15 | 36
Data Analysis | 2021-08-08 | 2021-12-21 | 136

## Data Collection Geography
Data Collection Notes - Smriti
S.No. | NYC Date | NYC Start Time | NYC End Time | UTC Date | UTC Start Time | UTC End Time | Area | Location Start | Location End | Store Names
1 | 2021-08-06 | 16:06 | 16:18 | 2021-08-06 | 20:06 | 20:18 | SoHo | W 4th and Broadway (along Broadway) | Prince St & Broadway | Duane Reade, Equinox, Sour Patch, Swatch, Urban Outfitters, Casper, Adidas, Crate & Barrel, American Eagle, The North Face, Verizon, Forever21, And Other Stories, Hugo Boss
2 | 2021-08-06 | 16:20 | 16:22 | 2021-08-06 | 20:20 | 20:22 |  | Prince Street Corner | - | Equinox, Hugo Boss
3 | 2021-08-06 | 16:30 | 16:32 | 2021-08-06 | 20:30 | 20:32 |  | Prince St and West Broadway | Prince & Wooster | Coach, Cole Haan, Marc Jacobs, Faherty, Untuckit (And a Museum which could be a potential hit)
4 | 2021-08-06 | 16:35 | 16:37 | 2021-08-06 | 20:35 | 20:37 |  | Prince & Wooster | Prince & Greene | Pleats Please/ Issey Miyake, LaCoste, Nars Cosmetics, Sandro SoHo, Polo Ralph Lauren, David Yurman, John Hardy, Farm Rio, Camper
5 | 2021-08-06 | 16:42 | 16:45 | 2021-08-06 | 20:42 | 20:45 |  | Prince & Greene | Prince & Broadway | Apple Store, Louis Vuitton, Miu Miu, Falconeri, Moncler, Mango, Prada,
6 | 2021-08-06 | 16:50 | 17:00 | 2021-08-06 | 20:50 | 21:00 |  | Prince & Broadway (along Broadway) | Broadway & Broome | Mango, Converse, Sephora, Uniqlo, Steve Madden, Nike, Lululemon, Foot Locker, Brandy Melville, H&M, All Saints, Zara, Bloomingdale's, Levis (And Museum of Ice Cream which could be a potential hit)
7 | 2021-08-06 | 17:36 | 17:49 | 2021-08-06 | 21:36 | 21:49 | Times Square | from 7th ave (stepped seating area) forever 21 to H&M | - | Forever 21, Express Outlet, Disney Store, Duane Reade, Gap, Citizen Watch, H&M, Verizon, MAC Cosmetics
8 | 2021-08-06 | 17:50 | 18:04 | 2021-08-06 | 21:50 | 22:04 |  | Opp side Steve Madden store to CVS | - | Steve Madden, AT&T, Skechers, Ray Ban, Tissot, Sephora, T-Mobile, American Eagle, Rhone, Inglot, CVS, Duane Reade, GNC, Verizon
9 | 2021-08-06 | 20:50 | 20:54 | 2021-08-07 | 0:50 | 0:54 | Downtown Brooklyn (along Fulton Street) | Jay St and Fulton St | Lawrence and Fulton | Gap, Duane Reade, Ann Taylor, T-Mobile
10 | 2021-08-06 | 20:55 | 20:57 | 2021-08-07 | 0:55 | 0:57 |  | Lawrence St and Fulton | Bridge and Fulton | The Children's Place, Foot Locker, Banana Republic, Macy's, American Eagle, Steve Madden, MAC Cosmetics
11 | 2021-08-06 | 20:58 | 21:00 | 2021-08-07 | 0:58 | 1:00 |  | Bridge and Fulton | Duffield and Fulton | H&M, TJ Maxx. Nordstrom Rack, Old Navy, Aldo, Verizon, Adidas
12 | 2021-08-06 | 21:01 | 21:04 | 2021-08-07 | 1:01 | 1:04 |  | Elm and Fulton | Bond and Fulton | Bank of America, AT&T, T-Mobile, Swarovski, Champ Sports, Express
13 | 2021-08-06 | 21:05 | 21:08 | 2021-08-07 | 1:05 | 1:08 |  | City Point Brooklyn |  | Casper, Target, Trader Joes
0:12
0:02
0:02
0:02
0:03
0:10
0:13
0:14
0:04
0:02
0:02
0:03
|  |  | 0:03 |  |  | 72

## Sheet1
Capstone Announcement | 2021-06-15 | 2021-06-15 | 1
Problem Definition | 2021-06-15 | 2021-06-28 | 14
Literature Review on previous works | 2021-06-28 | 2021-08-10 | 44
Background Research on Beacon Technology | 2021-06-28 | 2021-08-31 | 65
First Report and Presentation | 2021-07-06 | 2021-07-06 | 1
Research on Provider Companies and Beacon Unique ID | 2021-06-28 | 2021-08-31 | 65
Studying Information Flow Ecosystem | 2021-07-07 | 2021-08-31 | 56
Product Demos | 2021-07-15 | 2021-08-31 | 48
Database Collection Server Development | 2021-08-01 | 2021-08-05 | 5
Data Collection | 2021-08-04 | 2021-11-30 | 119
Second Report and Presentation | 2021-08-10 | 2021-08-10 | 1
App Modification | 2021-08-11 | 2021-09-15 | 36
Data Analysis | 2021-08-08 | 2021-12-21 | 136

## Sheet2
S.NO. | Company Names | Parent Company | Example UUID
1 | BlueCats | Plus Location Systems | 61687109-905f-4436-91f8-e602f514c96d
2 | Bluebar | BlueSense | a0b13730-3a9a-11e3-aa6e-0800200c9a66
3 | Estimote |  | b9407f30-f5f8-466e-aff9-25556b57fe6d
4 | Gelo |  | 11e44f09-4ec4-407e-9203-cf57a50fbce0
5 | Glimworm |  | 74278bda-b644-4520-8f0c-720eaf059935
6 | Gimbal | Qualcomm
7 | Kontakt |  | F7826DA6-4FA2-4E98-8024-BC5B71E0893E
8 | Sensorberg |  | 73676723-7400-0000-FFFF
9 | Sonic Notify
10 | Sensoro |  | 23A01AF0-232A-4518-9C0E-323FB773F5EF
11 | indoors
12 | Footmark
13 | Bluvision (Beeks Plus) | HID Global
14 | Aruba Bluetooth Beacons | HP | 4152554E-F99B-4A3B-86D0-947070693A78
15 | Em Microelectric | The Swatch Group Ltd. | 699EBC80-E1F3-11E3-9A0F-0CF3EE3BC012
16 | Bytereal
17 | Minew |  | 5dc33487f02e477d4058 (namespace id) ac233f251235(instance id)
18 | Ebyte
19 | 95power
20 | Skylab |  | FDA50693A4E24FB1AFCFC6EB07647825 (can be changed)
21 | Radioland
22 | Seekcy | 苏州寻息电子
23 | Bright beacon | 智石
24 | Sensoro | 升哲科技
25 | April Brother | 四月兄弟
26 | xBeacon | 深圳市蓝科迅通科技有限公司
27 | Accent | Accent Systems | 574f524c-4420-5348-4f50-50494e4700 0004 0003
28 | Avvel International |  | EBEFD083-70A2-47C8-9837-E7B5634DF524
29 | Apple AirLocate | Apple | E2C56DB5-DFFB-48D2-B060-D0F5A71096E0
30 | Ubudu |  | F2A74FC4-7625-44DB-9B08-CB7E130B2029
31 | Ubudu |  | 11118A8E-34EC-4326-B21E-9B35F22F405B
32 | Ubudu |  | E16E8A8E-34EC-4326-B21E-9B35F22F405B
33 | Passkit |  | 19D5F76A-FD04-5AA3-B16E-E93277163AF6
34 | Onyx beacon |  | 20CAE8A0-A9CF-11E3-A5E2-0800200C9A66
35 | RadBeacon/Radius Network |  | 2F234454-CF6D-4A0F-ADF2-F4911BA9FFA6/ 52414449-5553-4E45-5457-4F524B53434F
36 | Smartbeacon |  | 85FC11DD-4CCA-4B27-AFB3-876854BB5C3B
37 | Roximity |  | 8DEEFBB9-F738-4297-8040-96668BB44281
38 | BlueUp |  | ACFD065e-C3C0-11E3-9BBE-1A514932AC01
37 | RedBear |  | B0702980-A295-A8AB-F734-031A98A512DE/5AFFFFFF-FFFF-FFFF-FFFF-FFFFFFFFFFFF
38 | Beaconinside |  | F0018B9B-7509-4C31-A905-1A27D39C003C
39 | Open Beacon |  | AA6062F0-98CA-4211-8EC4-193EB73CEBE6
40 | Twocanoes |  | 92AB49BE-4127-42F4-B532-90FAF1E26491
41 | EasiBeacon/Beaconic |  | EBEFD083-70A2-47C8-9837-E7B5634DF524
42 | SB Legacy/shopnow |  | D57092AC-DFAA-446C-8EF3-C81AA22815B5
43 | Apple AirLocate |  | 5A4BCFCE-174E-4BAC-A814-092E77F6B7E5
44 | Estimote virtual beacon (iOS) |  | 8492E75F-4FD6-469D-B132-043FE94921D8
45 | Estimote virtual beacon (Mac) |  | 08D4A950-80F0-4D42-A14B-D53E063516E6
46 | RecoBean |  | 24DDF56411-8CF1-440C -C5B1-4B44-B512-1370F02D74DE
47 | Stick n Find
48 | Todd/Todally
49 | Omni access stellar | Alcatel lucent | 504F4C45-5354-4152-0000-0[0…]00
50 | Alcatel lucent
51 | SXSW |  | d77657c4-52a7-426f-b9d0-d71e10798c8a
52 | Motorola MPact |  | fe913213-b311-4a42-8c16-47faeac938db
53 | Aerohive |  | 4165726f-6869-7665-4e65-74776f726b73

## Sheet2 (2)
BEACON MANUFACTURERS AND DEFAULT UUIDS
S.NO. | BEACONS | PARENT COMPANY | POTENTIAL UUID | KNOWN CLIENTELE
1 | BlueCats | Plus Location Systems | 61687109-905f-4436-91f8-e602f514c96d
2 | Bluebar | BlueSense | a0b13730-3a9a-11e3-aa6e-0800200c9a66
3 | Estimote | Estimote | b9407f30-f5f8-466e-aff9-25556b57fe6d | Amazon, Nike, Apple, Hyatt, FedEx, Coca Cola, NASA
4 | Estimote virtual beacon (iOS) |  | 8492E75F-4FD6-469D-B132-043FE94921D8
5 | Estimote virtual beacon (Mac) |  | 08D4A950-80F0-4D42-A14B-D53E063516E6
6 | Apple AirLocate | Apple | E2C56DB5-DFFB-48D2-B060-D0F5A71096E0
7 | Apple AirLocate |  | 5A4BCFCE-174E-4BAC-A814-092E77F6B7E5
8 | Gelo | GeLo Inc. | 11e44f09-4ec4-407e-9203-cf57a50fbce0
9 | Glimworm | Glimworm Beacons | 74278bda-b644-4520-8f0c-720eaf059935
10 | Kontakt | Kontakt.io | F7826DA6-4FA2-4E98-8024-BC5B71E0893E
11 | Sensorberg | Sensorberg | 73676723-7400-0000-FFFF
12 | Sensoro | Sensoro | 23A01AF0-232A-4518-9C0E-323FB773F5EF
13 | Aruba Bluetooth Beacons | HP | 4152554E-F99B-4A3B-86D0-947070693A78
14 | Em Microelectric | The Swatch Group Ltd. | 699EBC80-E1F3-11E3-9A0F-0CF3EE3BC012
15 | Minew | Minew | Namespace ID: 5dc33487f02e477d4058 Instance ID: ac233f251235
16 | Skylab | Skylab | FDA50693A4E24FB1AFCFC6EB07647825
17 | Accent | Accent Systems | 574f524c-4420-5348-4f50-50494e4700 0004 0003
18 | Avvel X | Avvel International | EBEFD083-70A2-47C8-9837-E7B5634DF524
19 | Ubudu | Ubudu | F2A74FC4-7625-44DB-9B08-CB7E130B2029
20 | Ubudu |  | 11118A8E-34EC-4326-B21E-9B35F22F405B
21 | Ubudu |  | E16E8A8E-34EC-4326-B21E-9B35F22F405B
22 | RadBeacon | Radius Networks | 2F234454-CF6D-4A0F-ADF2-F4911BA9FFA6 / 52414449-5553-4E45-5457-4F524B53434F
23 | Smartbeacon | Smart Beacon | 85FC11DD-4CCA-4B27-AFB3-876854BB5C3B
24 | Roximity | CabinetM | 8DEEFBB9-F738-4297-8040-96668BB44281
25 | BlueUp | BlueUp | ACFD065e-C3C0-11E3-9BBE-1A514932AC01
26 | RedBear | Red Bear Co. Ltd. | B0702980-A295-A8AB-F734-031A98A512DE / 5AFFFFFF-FFFF-FFFF-FFFF-FFFFFFFFFFFF
27 | Beaconinside | BEACONinside | F0018B9B-7509-4C31-A905-1A27D39C003C
28 | Open Beacon |  | AA6062F0-98CA-4211-8EC4-193EB73CEBE6
29 | Twocanoes | TwoCanoes | 92AB49BE-4127-42F4-B532-90FAF1E26491
30 | EasiBeacon/Beaconic | Beaconic | EBEFD083-70A2-47C8-9837-E7B5634DF524
31 | SB Legacy |  | D57092AC-DFAA-446C-8EF3-C81AA22815B5
32 | RecoBean | RECO | 24DDF56411-8CF1-440C -C5B1-4B44-B512-1370F02D74DE
33 | Omni Access Stellar | Alcatel Lucent | 504F4C45-5354-4152-0000-0[0…]00
34 | Passkit | Passkit | 19D5F76A-FD04-5AA3-B16E-E93277163AF6
35 | Onyx beacon | Onyx | 20CAE8A0-A9CF-11E3-A5E2-0800200C9A66
36 | SXSW | SXSW | d77657c4-52a7-426f-b9d0-d71e10798c8a
37 | MPact | Motorola | fe913213-b311-4a42-8c16-47faeac938db
38 | Aerohive | Aerohive | 4165726f-6869-7665-4e65-74776f726b73
39 | Gimbal | Qualcomm | N/A
40 | Sonic Notify | Sonic Notify | N/A
41 | Footmarks | Footmarks | N/A
42 | Bluvision (Beeks Plus) | HID Global | N/A
43 | Bytereal | Bytereal | N/A
44 | Ebyte | Chengdu Ebyte Electronic Technology Co. Ltd. | N/A
45 | 95power | 95Power | N/A
46 | Radioland | Shenzhen Radioland Technology Co. Ltd. | N/A
47 | Seekcy | 苏州寻息电子 | N/A
48 | Bright beacon | 智石 | N/A
49 | April Brother | 四月兄弟 | N/A
50 | xBeacon | 深圳市蓝科迅通科技有限公司 | N/A
51 | Stick'N'Find | UMD | N/A

## Sheet5
List of
S.No. | Beacon Type | Detected UUIDs | Count | Manufacturing Companies
1 | iBeacon | 5993a94c-7d97-4df7-9abf-e493bfd5d000 | 2290 | N/A
2 | iBeacon | 504f4c45-5354-4152-0000-000000000000 | 740 | Alcatel Lucent
3 | iBeacon | d77657c4-52a7-426f-b9d0-d71e10798c8a | 618 | SXSW
4 | iBeacon | 50765cb7-d9ea-4e21-99a4-fa879613a492 | 399 | N/A
5 | iBeacon | 8a21c76b-74e3-4341-92be-33fcfdefdd63 | 312 | N/A
6 | iBeacon | 74278bda-b644-4520-8f0c-720eaf059935 | 169 | Glimworm
7 | iBeacon | 7aa9f224-d71e-4758-8f60-aa013261b9ac | 161 | N/A
8 | iBeacon | 2686f39c-bada-4658-854a-a62e7e5e8b8d | 153 | N/A
9 | iBeacon | 00009999-0000-1000-8000-00177a000002 | 94 | N/A
10 | iBeacon | e2c56db5-dffb-48d2-b060-d0f5a71096e0 | 90 | Apple Air Locate
11 | iBeacon | a65a5678-992b-4f30-39f2-1e8a502339d8 | 73 | N/A
12 | iBeacon | b0462602-cbf5-4abb-87de-b05340dccbc0 | 70 | N/A
13 | iBeacon | fe913213-b311-4a42-8c16-47faeac938db | 47 | Motorola Mpact
14 | iBeacon | 307e9194-9fe3-4412-ba98-6e816161a379 | 46 | N/A
15 | iBeacon | 4165726f-6869-7665-4e65-74776f726b73 | 37 | Aerohive
16 | iBeacon | 9eb353a0-69b6-4947-b710-bae643c8bca5 | 35 | N/A
17 | iBeacon | a8d278e4-35b5-44ef-9cac-0f3fc511fe3e | 31 | N/A
18 | iBeacon | 1b3220c5-a80b-4421-9c56-8efbe7696da7 | 29 | N/A
19 | iBeacon | 6ab357ac-96dd-4d5e-a606-b9dd64c570c7 | 28 | N/A
20 | iBeacon | 6ca0c73c-f8ec-4687-9112-41dcb6f28879 | 27 | N/A
21 | iBeacon | ffff6f1b-ff09-cbff-8a00-ff8aff00ff03 | 26 | N/A
22 | iBeacon | 9d9c61b3-2786-44d9-9ec0-bfe20a880f0d | 25 | N/A
23 | iBeacon | 53546f1b-ff09-ce82-80ff-af80ffffaf03 | 20 | N/A
24 | iBeacon | fda50693-a4e2-4fb1-afcf-c6eb07647825 | 17 | Skylab
25 | iBeacon | ffff6f1b-ff09-c9ff-ff60-9affff609a03 | 17 | N/A
26 | iBeacon | b8ba3d72-9fd6-4ca1-89f6-d0da18de8375 | 16 | N/A
27 | iBeacon | 53546f1b-ff09-ca82-8a00-ff8aff00ff03 | 15 | N/A
28 | iBeacon | 53546f1b-ff09-fc82-ffe0-00ffffe00003 | 15 | N/A
29 | iBeacon | ffff6f1b-ff09-cfff-80ff-af80ffffaf03 | 14 | N/A
30 | iBeacon | 53546f1b-ff09-0282-5f30-ff5fff30ff03 | 14 | N/A
31 | iBeacon | 53546f1b-ff09-cc82-ffe0-00ffffe00003 | 14 | N/A
32 | Altbeacon | 5241444e-5441-424c-4553-455256494345 | 13 | N/A
33 | iBeacon | 53546f1b-ff09-0482-ff10-40ffff104003 | 13 | N/A
34 | iBeacon | ffff6f1b-ff09-c5ff-5f30-ff5fff30ff03 | 13 | N/A
35 | iBeacon | 53546f1b-ff09-d082-5f30-ff5fff30ff03 | 13 | N/A
36 | iBeacon | ffff6f1b-ff09-fbff-8a00-ff8aff00ff03 | 13 | N/A
37 | iBeacon | ffff6f1b-ff09-c7ff-ff10-40ffff104003 | 12 | N/A
38 | iBeacon | f7f489e9-c07e-41b0-beab-a24ce4d49faa | 11 | N/A
39 | iBeacon | ffff6f1b-ff09-03ff-5f30-ff5fff30ff03 | 11 | N/A
40 | iBeacon | ffff6f1b-ff09-cdff-ffe0-00ffffe00003 | 11 | N/A
41 | iBeacon | e60fdc20-9e42-11e9-b475-0800200c9a66 | 10 | N/A
42 | iBeacon | f1eabf09-e313-4fcd-80df-67c779763888 | 10 | N/A
43 | iBeacon | dc4f4e8e-d7b0-4e72-b609-97f2796149f9 | 9 | N/A
44 | iBeacon | 4b1c5e0f-ccd0-401d-81e1-a970adbd9640 | 9 | N/A
45 | iBeacon | e20a39f4-73f5-4bc4-1864-17d1ad07a962 | 8 | N/A
46 | iBeacon | b8fed863-9f1c-447c-8f82-df0c2e067dea | 8 | N/A
47 | iBeacon | 53546f1b-ff09-c882-ff60-9affff609a03 | 8 | N/A
48 | iBeacon | 53546f1b-ff09-fa82-8a00-ff8aff00ff03 | 8 | N/A
49 | iBeacon | f000f0c0-0451-4000-b000-000000000000 | 8 | N/A
50 | iBeacon | ffff6f1b-ff09-01ff-80ff-af80ffffaf03 | 7 | N/A
51 | iBeacon | ffff6f1b-ff09-fdff-ffe0-00ffffe00003 | 7 | N/A
52 | iBeacon | 53546f1b-ff09-f882-ff60-9affff609a03 | 7 | N/A
53 | iBeacon | 53546f1b-ff09-d282-ff10-40ffff104003 | 6 | N/A
54 | iBeacon | ffff6f1b-ff09-f9ff-ff60-9affff609a03 | 6 | N/A
55 | iBeacon | e1f54e02-1e23-44e0-9c3d-512eb56adec9 | 6 | Estimote
56 | iBeacon | 53546f1b-ff09-c682-ff10-40ffff104003 | 6 | N/A
57 | Altbeacon | 2f234454-cf6d-4a0f-adf2-f4911ba9ffa6 | 6 | Radius Networks
58 | iBeacon | 53546f1b-ff09-f682-ff10-40ffff104003 | 6 | N/A
59 | iBeacon | 12345678-1234-1234-1234-123456789123 | 6 | N/A
60 | iBeacon | ffff6f1b-ff09-c3ff-80ff-af80ffffaf03 | 5 | N/A
61 | iBeacon | ffff6f1b-ff09-c1ff-ffe0-00ffffe00003 | 5 | N/A
62 | iBeacon | ffff6f1b-ff09-05ff-ff10-40ffff104003 | 5 | N/A
63 | iBeacon | f000face-0451-4000-b000-000000000000 | 5 | N/A
64 | iBeacon | ffff6f1b-ff09-f3ff-80ff-af80ffffaf03 | 5 | N/A
65 | iBeacon | 53546f1b-ff09-fe82-80ff-af80ffffaf03 | 4 | N/A
66 | iBeacon | ffff6f1b-ff09-d5ff-ff60-9affff609a03 | 4 | N/A
67 | iBeacon | 53546f1b-ff09-f282-80ff-af80ffffaf03 | 3 | N/A
68 | iBeacon | ffff6f1b-ff09-f7ff-ff10-40ffff104003 | 2 | N/A
69 | iBeacon | 211c0407-f382-4699-9111-8b1223051903 | 2 | N/A
70 | iBeacon | bb865c82-49f0-4df9-b8f5-75a406405cbb | 2 | N/A
71 | iBeacon | 18a54793-5c75-49ae-af6d-3edda84dffc3 | 2 | N/A
72 | iBeacon | ef090000-11d6-42ba-93b8-9dd7ec090aa9 | 1 | N/A
73 | iBeacon | 56db0365-a001-4062-9e4d-499d3b8eccf3 | 1 | N/A
74 | iBeacon | 53546f1b-ff09-c482-5f30-ff5fff30ff03 | 1 | N/A
75 | iBeacon | 952a3af1-a1f2-1e50-4c4f-b2656ad18510 | 1 | N/A
76 | Eddystone | x10b851227a32ed75fbcc | 6 | N/A
77 | Eddystone | 0x85ceeb822284d5870c3a | 67 | N/A
78 | Eddystone | 0xb2e5fc49d46042b9893c | 190 | N/A
79 | Eddystone | 0xc4abe71156a5fa70a23f | 1 | N/A
80 | Eddystone | 0xf86410c4c588a9cec5f1 | 1 | N/A